## Handover checklist
[ YOUR STUDIO NAME ]
HANDOVER CHECKLIST AND SNAG LIST
Walk the site with the client. Mark each check OK or Snag; write every snag down with a date to fix it. Both sign at the end: items not on this list are service calls under the warranty, not a reason to hold the final payment.
Client
Site
Handover date
# | CHECK | OK / SNAG | SNAG — WHAT EXACTLY | FIX BY | FIXED ON | CLIENT INITIALS
KITCHEN
1 | Every shutter aligned, gaps even, no rubbing
2 | Soft-close hinges and channels close fully
3 | Baskets and pull-outs run without catching
4 | Sink and tap: run for 5 minutes, no leak below
5 | Countertop joints sealed; no chips at the edges
6 | Chimney and hob points tested
WARDROBES AND STORAGE
7 | Shutters level and closing flush
8 | Locks work, with keys handed over
9 | Drawers and internal accessories as per BOQ
10 | Loft shutters open without hitting the ceiling
11 | Edge banding complete, no lifting
ELECTRICAL
12 | Every switch and socket tested
13 | Every light fixture working
14 | MCBs labelled room by room
15 | AC and geyser points tested under load
CEILING, WALLS AND FLOOR
16 | No cracks at ceiling joints or along the cove
17 | Paint even under daylight and under the ceiling lights
18 | No patches, roller marks or paint on switches and skirting
19 | Flooring: no hollow tiles, grout complete
BATHROOMS
20 | No leak at any joint after running water
21 | Floor drains towards the outlet
22 | Accessories fixed firmly, as per BOQ
HANDED OVER
23 | Keys for every lock, counted
24 | Warranty cards and invoices for hardware and appliances
25 | Care instructions for laminates, veneer and stone
26 | Electrical layout as built
27 | Site cleaned, debris removed
Snags open
| Designer: ______________________ Date: __________ |  | Client: ______________________ Date: __________
Format by Houscade — houscade.in. Free to use and change.